FARMERS FACTORY ERP v2

Order-to-Delivery System

Implementation Master Plan

10 Modules  ·  7 Phases  ·  22 Weeks

Stack: React + TypeScript + Supabase + React Native + Vite

Prepared: May 2026  |  Author: IGO AI Junior Associate

# Executive Summary

This document is the master implementation plan for the FFERPv2 Order-to-Delivery revamp for Farmers Factory. It covers 10 new or revamped modules that automate the complete daily cycle from customer order intake through procurement, hub receiving, inventory management, delivery dispatch, and vendor bill approval.

The existing ERP application (React + TypeScript + Vite + Supabase) already has foundational modules for purchase, warehouse, logistics, and sales. This revamp adds an automated, event-driven layer on top using Supabase Realtime, pg_cron, Edge Functions, and a React Native scanner app extension.

## Daily Operational Cycle

- 10:00 AM – 11:00 PM: Orders flow in via 4 channels (Website, Mobile, WhatsApp, Manual)

- 11:59 PM: Supabase pg_cron triggers EOD PO Engine — generates purchase orders per hub based on confirmed orders minus current stock

- 12:00 AM: POs route to on-shift Purchase Executive queue

- 06:00 AM – 10:00 AM: Purchase Executive procures from vendors; boxes arrive at hubs

- 10:00 AM – 12:00 PM: Hub Manager scans boxes in via mobile scanner app; QC check

- 01:00 PM – 04:00 PM: Packing team groups boxes into delivery packs; dispatch scan

- 04:00 PM – 08:00 PM: Drivers deliver packs; confirm delivery via mobile app

- Post-delivery: PO bills auto-generated; approval chain ff_gm → Admin → CEO → vendor payment

## Build vs Revamp Summary

- M01 Centralized Order Hub — New Build

- M02 Geo Hub Assignment Engine — New Build

- M03 FF GM Command Dashboard — New Build

- M04 EOD PO Engine — New Build (revamps AutoPOPage.tsx)

- M05 Purchase Executive Portal — Revamp of FreshPurchaseDashboard.tsx

- M06 Barcode/QR Generation System — New Build

- M07 Hub Manager Scanner App — New Build (extends mobile-app)

- M08 Smart Inventory Management — Revamp of InventoryDashboard.tsx

- M09 Delivery & Distribution Module — Revamp of DriverView.tsx + LogisticsDashboard.tsx

- M10 PO Bill & Approval Workflow — New Build (revamps AutoBillPage.tsx)

# Module Overview

All 10 modules with build type, phase, and technology stack:

| ID | Module Name | Type | Phase | Key Technologies |
| --- | --- | --- | --- | --- |
| M01 | Centralized Order Hub | New Build | Phase 1 | Supabase Realtime, WhatsApp Business API, Webhooks, TanStack Query v5 |
| M02 | Geo Hub Assignment Engine | New Build | Phase 1 | Google Maps Geocoding API, PostGIS, Haversine calc, Supabase Edge Function |
| M03 | FF GM Command Dashboard | New Build | Phase 2 | Supabase Realtime, Recharts, Role: ff_gm, TanStack Query v5 |
| M04 | EOD PO Engine | New Build | Phase 2 | pg_cron (23:59), Supabase Edge Function, PostgreSQL RPC |
| M05 | Purchase Executive Portal | Revamp | Phase 3 | Supabase Realtime, Shift logic, Role: purchase_manager |
| M06 | Barcode/QR Generation System | New Build | Phase 3 | QRCode.js, JsBarcode, jsPDF, Supabase Storage |
| M07 | Hub Manager Scanner App | New Build | Phase 4 | React Native, Expo Camera, Offline Queue (extends existing) |
| M08 | Smart Inventory Management | Revamp | Phase 4 | Supabase Realtime, PostgreSQL triggers, TanStack Query v5 |
| M09 | Delivery & Distribution Module | Revamp | Phase 5 | React Native, Barcode scan, Expo Location, Role: driver |
| M10 | PO Bill & Approval Workflow | New Build | Phase 6 | Multi-step approval chain, Supabase RLS, Email notifications |

# Module Detail Specifications

M01 — Centralized Order Hub

Type: New Build

Phase: 1 (Weeks 1–3)

Role Access: ff_gm, back_office, tele_caller

### New Files to Create

- src/pages/ff/orders/OrderHubPage.tsx — Main order hub with 4-channel feed

- src/pages/ff/orders/components/OrderChannelFeed.tsx — Live order stream with channel badges

- src/pages/ff/orders/components/ManualOrderForm.tsx — Manual order entry form

- src/hooks/useOrders.ts — TanStack Query hooks for orders

- supabase/functions/whatsapp-webhook/ — Meta webhook receiver + order parser

### Key Features

- Receives orders from 4 channels: Website webhook, Mobile Realtime, WhatsApp API, Manual form

- Unified order feed with channel badges, filter, and search

- Order status lifecycle: new → confirmed → processing → dispatched → delivered

- WhatsApp template message parsing (structured button flow, not free-text NLP)

- Real-time feed using Supabase Realtime subscription on orders table

- Auto-triggers hub assignment (M02) on order creation

M02 — Geo Hub Assignment Engine

Type: New Build

Phase: 1 (Weeks 1–3)

Trigger: Database trigger on orders INSERT

### New Files to Create

- supabase/functions/assign-hub-to-order/ — Geocodes address, calculates Haversine distance, assigns hub

- src/pages/ff/orders/components/HubAssignmentMap.tsx — Map view of assignments

- supabase/migrations/add_hub_geolocation.sql — Adds lat/lng to hubs table, enables PostGIS

### Key Features

- Geocodes customer address on order creation via Google Maps Geocoding API

- Haversine distance calculation to all active hubs

- Auto-assigns nearest hub; fallback to HQ if > 15km radius

- Hub capacity guard: if hub daily limit exceeded, reassigns to next nearest

- Manual hub override available to ff_gm and back_office

M03 — FF GM Command Dashboard

Type: New Build

Phase: 2 (Weeks 4–6)

Role Access: ff_gm

### New Files to Create

- src/pages/ff/gm/GMDashboardPage.tsx — Main GM dashboard

- src/pages/ff/gm/components/LiveOrderFeed.tsx — Real-time order stream

- src/pages/ff/gm/components/POPreviewTable.tsx — Hourly-refreshed PO preview

- src/pages/ff/gm/components/HubStatusGrid.tsx — Per-hub status cards

- src/pages/ff/gm/components/EarlyApprovalPanel.tsx — Pre-11:59PM PO approval

### Key Features

- Live order feed via Supabase Realtime channel subscription

- Hub-wise order summary cards with total quantity and revenue

- Auto-refreshed PO preview (updated hourly by background query)

- Early PO approval before 23:59 cron (optional manual trigger)

- Alert panel: unassigned orders, low stock, SLA breaches from existing IGO ERP

- Revenue projection for current day based on confirmed orders

M04 — EOD PO Engine

Type: New Build (revamps AutoPOPage.tsx)

Phase: 2 (Weeks 4–6)

Trigger: pg_cron: 59 23 * * *

### New Files to Create

- supabase/functions/eod-po-generator/ — Core PO generation Edge Function

- supabase/migrations/create_purchase_orders.sql — purchase_orders + po_items tables

- src/pages/ff/purchase/PODetailPage.tsx — PO detail view

### Key Features

- pg_cron job fires at 23:59 daily

- Per-hub PO generation: delta = SUM(confirmed order qty) - current inventory qty

- Groups PO line items by product category and preferred vendor

- PO status machine: draft → pending_approval → approved → dispatched

- Handles zero-inventory edge case: PO quantity = full order quantity

- Notification to ff_gm on PO generation (email + in-app alert)

M05 — Purchase Executive Portal

Type: Revamp — FreshPurchaseDashboard.tsx + AutoPOPage.tsx

Phase: 3 (Weeks 7–10)

Role Access: purchase_manager

### Files to Create/Modify

- src/pages/ff/purchase/PurchaseExecutivePortal.tsx — New portal page

- src/pages/ff/purchase/components/POQueueTable.tsx — Shift-based PO queue

- src/pages/ff/purchase/components/ShiftHandoverPanel.tsx — Handover notes

- src/hooks/usePurchaseShift.ts — Shift state and PO assignment logic

### Key Features

- Day-start queue: POs routed to on-shift executive at 12:00 AM

- Shift-based assignment (morning/afternoon/night shifts)

- Mark PO items as procured with actual cost entry

- Shift handover notes and pending item transfer to next shift

- Escalation alert if PO not actioned within 2 hours of shift start

- Daily target vs. actual procurement performance tracking

M06 — Barcode/QR Generation System

Type: New Build

Phase: 3 (Weeks 7–10)

### New Files to Create

- src/pages/ff/barcode/BarcodeGeneratorPage.tsx — Main barcode generation page

- src/pages/ff/barcode/components/BoxLabelPDF.tsx — PDF label renderer (jsPDF)

- src/pages/ff/barcode/components/BatchPrintPanel.tsx — Batch label printing

- src/hooks/useBoxLabels.ts — Box label state management

- supabase/migrations/create_boxes.sql — boxes table

### Key Features

- Auto-generate box record on PO line item receipt confirmation

- Unique box ID format: FF-{HUB}-{DATE}-{SEQ} (e.g., FF-KLY-20260523-001)

- QR code contains JSON metadata (product, weight, hub, PO ref)

- Barcode encodes box ID using Code128 format via JsBarcode

- PDF label: product name, weight, PO reference, hub name, QR + barcode

- Label stored in Supabase Storage for reprinting; batch print mode for multiple boxes

M07 — Hub Manager Scanner App (React Native)

Type: New Build — extends mobile-app/

Phase: 4 (Weeks 11–14)

Role Access: hub_manager (new role)

### New Files to Create

- mobile-app/src/screens/hub/HubScannerScreen.tsx — Barcode/QR scanner (extends CameraComponent.tsx)

- mobile-app/src/screens/hub/ReceivedBoxesScreen.tsx — Today's received boxes list

- mobile-app/src/screens/hub/InventoryScreen.tsx — Real-time hub inventory view

- mobile-app/src/hooks/useBarcodeScanner.ts — Scanner state and decode logic

- mobile-app/src/services/hubSyncService.ts — Extends offlineSyncService.ts for hub events

### Key Features

- Barcode/QR scan via Expo Camera (existing CameraComponent.tsx extended)

- Scan-to-receive: scan box barcode → inventory event +qty at hub

- QC pass/fail toggle on scan; reject logs QC record with optional photo

- Offline scan queue using existing offlineSyncService.ts — syncs when back online

- Hub manager dashboard: expected deliveries vs. received count for the day

- Wastage logging: scan a box → mark damaged/expired with reason code

M08 — Smart Inventory Management

Type: Revamp — InventoryDashboard.tsx + WastageManagement.tsx

Phase: 4 (Weeks 11–14)

### Files to Create/Modify

- src/pages/ff/inventory/SmartInventoryPage.tsx — New smart inventory dashboard

- src/pages/ff/inventory/components/StockMovementLog.tsx — Event log view

- src/pages/ff/inventory/components/WastagePrediction.tsx — Rolling 7-day trend

- supabase/migrations/create_inventory_events.sql — PostgreSQL trigger + inventory_log table

### Event Types (inventory_log.event_type)

- +receive — box scan at hub (M07)

- -dispatch — box leaves in delivery pack (M09)

- -wastage — box marked damaged/expired (M07)

- -qc_reject — box failed QC scan (M07)

- +return — undelivered box returned to hub (M09)

### Key Features

- Event-driven inventory updates via PostgreSQL trigger on inventory_log INSERT

- Trigger atomically updates inventory.qty_kg using event qty_delta

- Low stock alert at configurable min_threshold per product per hub

- Wastage trend analysis with rolling 7-day chart (Recharts)

- Stock reconciliation: expected vs. actual at end of each delivery cycle

M09 — Delivery & Distribution Module

Type: Revamp — DriverView.tsx + LogisticsDashboard.tsx + new mobile screens

Phase: 5 (Weeks 15–17)

### New Files to Create

- src/pages/ff/delivery/DeliveryPackingPage.tsx — Pack creation with box scanner

- src/pages/ff/delivery/DispatchDashboardPage.tsx — Dispatch overview

- mobile-app/src/screens/driver/DriverDeliveryScreen.tsx — Driver delivery manifest

- mobile-app/src/screens/driver/CustomerConfirmScreen.tsx — Delivery confirmation (OTP/photo)

- supabase/migrations/create_delivery_packs.sql — delivery_packs table

### Key Features

- Pack creation: group boxes into a named delivery pack per route/area

- Scan boxes into pack to verify correct items (barcode verification)

- Dispatch scan: pack leaves hub → inventory -dispatch event for each box

- Driver mobile app: view manifest, customer list, delivery sequence

- GPS tracking via Expo Location (existing mobile app)

- Customer delivery confirmation: OTP or photo signature capture

- Partial delivery: mark undelivered items with reason; return scan for undelivered boxes

M10 — PO Bill & Approval Workflow

Type: New Build (revamps AutoBillPage.tsx)

Phase: 6 (Weeks 18–20)

### New Files to Create

- src/pages/ff/billing/POBillDetailPage.tsx — Full bill detail view

- src/pages/ff/billing/BillApprovalQueuePage.tsx — Queue per role

- src/pages/ff/billing/components/ApprovalChainTimeline.tsx — Visual approval history

- supabase/functions/bill-approval-notify/ — Sends notifications on approval status change

- supabase/migrations/create_po_bills.sql — po_bills table with per-role status columns

### Threshold-Based Approval Routing

- Bills < Rs.10,000 — ff_gm approval only

- Bills Rs.10,000 – Rs.50,000 — ff_gm + admin approval

- Bills > Rs.50,000 — ff_gm + admin + ceo approval (full chain)

### Key Features

- Bill auto-created when purchase_orders status = fully_procured

- Each approver: approve / reject with mandatory comment

- Rejection notifies purchase executive to rectify and resubmit

- CEO approval → vendor payment instruction PDF generated

- Full audit trail: who approved, timestamp, IP address (Supabase RLS enforced)

- Dashboard view of pending approvals filtered by current user role

# 7-Phase Implementation Plan

Total estimated duration: 22 weeks. Phases can partially overlap where there are no blocking dependencies.

| Phase | Name | Weeks | Modules | Key Deliverables |
| --- | --- | --- | --- | --- |
| 1 | Foundation & Infrastructure | Wks 1-3 | M01, M02 | DB migrations (15 tables), RLS policies, ff_gm role, WhatsApp webhook, Geocoding Edge Function, Supabase Realtime channels, TanStack Query v5 install |
| 2 | GM Dashboard + EOD PO Engine | Wks 4-6 | M03, M04 | FF GM Command Dashboard with live feed, pg_cron 23:59 PO generator, PO preview table, early approval flow, eod-po-generator Edge Function |
| 3 | Purchase Portal + Barcode System | Wks 7-10 | M05, M06 | Purchase Executive portal with shift-based routing, QR/barcode generation, PDF label export, Supabase Storage for label archiving, shift handover logic |
| 4 | Hub Scanner + Smart Inventory | Wks 11-14 | M07, M08 | React Native hub scanner screens, offline scan queue (extends offlineSyncService.ts), event-driven inventory via PostgreSQL triggers, wastage + QC tracking |
| 5 | Delivery & Distribution | Wks 15-17 | M09 | Pack creation + dispatch workflow, DriverView revamp with barcode scan, driver mobile screens, GPS tracking, partial delivery + returns |
| 6 | PO Bill Approval Chain | Wks 18-20 | M10 | Multi-step bill approval (ff_gm -> admin -> ceo), threshold-based routing, audit trail, bill PDF export, vendor payment instruction, bill-approval-notify Edge Function |
| 7 | Integration Testing & Hardening | Wks 21-22 | All | E2E cycle test, load test Realtime (100+ concurrent), offline sync stress test, RLS audit, DB index optimization (hub_id, created_at, status), performance tuning |

# Database Schema — 15 New Tables

All 15 tables must be created via Supabase migrations before any module is built. RLS policies must be applied immediately after table creation. Green = PK, Purple = FK in the schema conventions.

| Table | Key Fields | Used By Module(s) |
| --- | --- | --- |
| orders | id, customer_id (FK), hub_id (FK), channel, status, total_amount, delivery_date, created_at | M01, M02, M03, M04 |
| order_items | id, order_id (FK), product_id (FK), qty, unit_price, status | M01, M04, M08 |
| customers | id, name, phone, address, lat, lng, whatsapp_id, created_at | M01, M02 |
| hubs | id, name, lat, lng, capacity_kg, is_active, manager_id (FK) | M02, M03, M07, M08 |
| purchase_orders | id, hub_id (FK), generated_at, status, approved_by (FK), total_cost | M04, M05, M06, M10 |
| po_items | id, po_id (FK), product_id (FK), qty_ordered, qty_received, unit_cost | M04, M05, M06 |
| inventory | id, hub_id (FK), product_id (FK), qty_kg, last_updated, min_threshold | M07, M08, M09 |
| inventory_log | id, inventory_id (FK), event_type, qty_delta, ref_id, created_at | M07, M08, M09 |
| boxes | id, box_code, po_item_id (FK), product_id (FK), weight_kg, qr_url, barcode_url, status | M06, M07, M09 |
| delivery_packs | id, hub_id (FK), driver_id (FK), route_date, status, dispatched_at | M09 |
| qc_records | id, box_id (FK), result, inspector_id (FK), photo_url, notes | M07, M08 |
| wastage_log | id, box_id (FK), reason, weight_kg, logged_by (FK), logged_at | M07, M08 |
| po_bills | id, po_id (FK), amount, gm_status, admin_status, ceo_status, vendor_paid, created_at | M10 |
| shift_logs | id, employee_id (FK), shift_type, start_time, end_time, hub_id (FK) | M05 |
| employee_targets | id, employee_id (FK), target_date, po_target, po_actual, hub_id (FK) | M05 |

# Edge Functions & Cron Jobs

## 1. whatsapp-webhook

Trigger: HTTP POST — Meta WhatsApp Business API webhook

Purpose: Receives WhatsApp message events, parses structured template responses, creates order record in Supabase

Key Logic: Verify Meta webhook signature → parse template payload → extract product + quantity → INSERT into orders + order_items → return 200 immediately

## 2. assign-hub-to-order

Trigger: Database trigger on orders table INSERT

Purpose: Auto-assign nearest available hub to every new order using geocoding + Haversine distance

Key Logic: Geocode customer.address via Google Maps API → calculate Haversine distance to all active hubs → rank by distance → check hub capacity → UPDATE orders.hub_id

## 3. eod-po-generator

Trigger: pg_cron: 59 23 * * * (23:59 daily)

Purpose: Generate purchase orders per hub for next-day procurement based on confirmed orders minus current inventory

Key Logic: SELECT confirmed orders grouped by hub + product → JOIN inventory for current stock → compute delta = orders - stock → INSERT purchase_orders + po_items → notify ff_gm

## 4. bill-approval-notify

Trigger: Database trigger on po_bills UPDATE

Purpose: Send notification to next approver in chain on each approval status change

Key Logic: Read new status → determine next approver role → send email + push notification → log to audit trail

## 5. inventory-event-processor

Trigger: Database trigger on inventory_log INSERT

Purpose: Atomically update inventory.qty_kg on each stock movement event and fire low-stock alerts

Key Logic: UPDATE inventory SET qty_kg = qty_kg + NEW.qty_delta → check vs min_threshold → if below threshold, INSERT into alerts table and notify hub_manager + ff_gm

## 6. check-sla-breach (extend existing)

Trigger: pg_cron: 0 * * * * (hourly — already exists)

Purpose: Extend existing IGO ERP SLA check to also monitor unactioned POs during procurement shifts

Key Logic: Add: SELECT purchase_orders WHERE status = pending_procurement AND created_at < NOW() - INTERVAL 2 hours → INSERT escalation alert

# Open Questions — Answered from Codebase Analysis

Six open questions from the Module Plan document have been answered based on the existing codebase review and architectural best practices:

## Q1: WhatsApp order format — free-text NLP or structured template?

Recommendation: Use Meta WhatsApp template messages with button flows (Product → Quantity → Confirm). This avoids NLP complexity, is faster to build, and produces structured payload data the webhook Edge Function can parse directly. Free-text NLP intent detection can be added as a Phase 7+ enhancement.

## Q2: Which geocoding API?

Recommendation: Google Maps Geocoding API. It provides the most accurate India address coverage, which is critical for correct hub assignment. Estimated cost: ~$5 per 1,000 geocode calls (on order creation events only). Add the API key to Supabase secrets. PostGIS extension (available on Supabase Pro) handles spatial queries for Haversine distance calculation.

## Q3: How many hubs, and do they have fixed product catalogs?

Based on existing HubManagementPage.tsx: all hubs handle the full product catalog by default. A hub_product_overrides table can be added later to restrict specific products per hub. For EOD PO generation, aggregate all confirmed orders per hub — purchase executive handles vendor routing per product category within their shift.

## Q4: Mobile scanner — new app or additional screens in existing mobile-app?

Add screens to the existing mobile-app/ React Native project. CameraComponent.tsx and offlineSyncService.ts are already built — M07 extends them. Add a new Hub navigation stack (HubScannerScreen, ReceivedBoxesScreen, InventoryScreen) gated behind the hub_manager role. No new app submission to app stores needed, saving significant overhead.

## Q5: Bill approval structure — always CEO or threshold-based?

Recommendation: Threshold-based routing. Bills < Rs.10,000 = ff_gm only. Bills Rs.10,000–Rs.50,000 = ff_gm + admin. Bills > Rs.50,000 = full chain (ff_gm + admin + ceo). Thresholds stored in a bill_approval_thresholds config table for easy adjustment. This prevents CEO bottleneck on small vendor bills while maintaining full governance on large purchases.

## Q6: Per-hub inventory or centralized with hub allocation?

Per-hub inventory is the correct architecture. The inventory table uses hub_id as a partition key matching the existing warehouse module pattern. A central SmartInventoryPage aggregates across hubs for the ff_gm. This avoids race conditions from centralized allocation and matches the physical reality: each hub receives, stores, and dispatches independently.

# New Routes to Add to App.tsx

- src/App.tsx: Add ff_gm to role constants (ALL_STAFF_ROLES / new FF_OPS_ROLES array)

- /ff-orders — OrderHubPage (roles: ff_gm, back_office, tele_caller)

- /ff-gm — GMDashboardPage (roles: ff_gm)

- /ff-purchase/portal — PurchaseExecutivePortal (roles: purchase_manager)

- /ff-purchase/po/:id — PODetailPage (roles: ff_gm, purchase_manager)

- /ff-barcode — BarcodeGeneratorPage (roles: ff_gm, purchase_manager)

- /ff-inventory/smart — SmartInventoryPage (roles: ff_gm, warehouse_manager)

- /ff-delivery/packing — DeliveryPackingPage (roles: warehouse_manager, ff_gm)

- /ff-delivery/dispatch — DispatchDashboardPage (roles: ff_gm, warehouse_manager)

- /ff-billing/po/:id — POBillDetailPage (roles: ff_gm, admin, ceo)

- /ff-billing/approvals — BillApprovalQueuePage (roles: ff_gm, admin, ceo)

# New npm Packages to Install

- qrcode — QR code generation for M06 (npm install qrcode)

- jsbarcode — Barcode generation for M06 (npm install jsbarcode)

- jspdf — PDF label export for M06 and M10 (npm install jspdf)

- @tanstack/react-query v5 — Already likely installed; verify version

- expo-barcode-scanner or expo-camera — For M07 mobile scanner (upgrade existing)

- @googlemaps/js-api-loader — For M02 hub assignment map visualization

This plan is the single source of truth before build begins. All 6 open questions are resolved. Begin with Phase 1: DB migrations + ff_gm role + WhatsApp webhook.